## Sheet1
Test Results | CR# | Problem | Fixes Location | Applied in Production
| 3945 | EMM Custodian Change multiple issues | 3945-EMM Custodian Change multiple issues | 2012-02-27
| 3919 | Add Reports to File Activities Association Screen | 3919-Add Reports to File Activities Association Screen | 2012-02-27
| 3941 | Increase Source Meet Activity Received field from 3900 to 5000 characters | 3941-Increase Source Meet Activity Received field from 3900 to 5000 characters | 2012-02-27
| 3948 | CFunds Expense Changes | 3948-CFunds Expense Changes | 2012-02-27 | Also fixes CHG0003936
| 3946 | Add Links to Files-Activities (parent) in the Attachments tab of Files | 3946-Add Links to Files-Activities (parent) in the Attachments tab of Files | 2012-02-27
| 3938 | Trying to delete an Incident that is related to a SPEC gets an error | 3938-Trying to delete an Incident that is related to a SPEC gets an error | 2012-02-27
| 3937 | New CFunds Category | 3937-New CFunds Category | 2012-02-27
| 3921 3930 | Add Paragraph and Activity link to CFMS Expense Screens | 3921, 3930 - Add Paragraph and Activity link to CFMS Expense Screens | 2012-02-27
| 3754 | CFunds Expense Desktop View Description too large | 3754-CFunds Expense Desktop View Description too large | 2012-02-27 | See Implementation.doc***
| 3863 | PART II - Reject or Recall should set file back to IC | 3863-PART II - Reject or Recall should set file back to IC.sql | 2012-02-27 | Additional changes that were needed.
ABOVE 10 PATCHES WERE MOVED FROM 5.0.4
| 3933 | Form 40 ROI Report doesn't print correctly | 3933-Form 40 ROI Report doesn't print correctly | 2012-03-07
| 3427 | New Offenses | 3427-New Offenses | 2012-03-07 | OLD CR stated that it needed to be done in Web as well… NEVER DONE BY RICHMOND.
| 3932 | Classification on Reports showing U instead of FOUO | 3932-Classification on Reports showing U instead of FOUO.sql | 2012-03-07
| 3304 | SSN wrong in LON (carry over from Legacy I2MS) | 3304-SSN wrong in LON (carry over from Legacy I2MS).sql | 2012-03-07 | OLD CR applied in 4.13.0 of Legacy, never carried over to WebI2MS. (Applied in Legacy on 30-Sep-2009).
| 3915 3961 3932 | IDP notes report changes | 3915, 3961, and 3932-IDP notes report changes.sql | 2012-03-07 | See Implementation.doc **
| 3961 3963 | AAPP ROI IDP Page Changes | 3961, 3963 - AAPP ROI IDP Page Changes | 2012-03-07
| 3822 | P0 Objects When more than one open testing | 3822-P0 Objects When more than one open testing.sql | 2012-03-07
| 3920 | Goto Tab for Checklist Items | 3920-Goto Tab for Checklist Items.sql | 2012-03-07
| 3947 | Missing EMM Filters | 3947-Missing EMM Filters.sql | 2012-03-07
| 4007 | Report Spec 1=1 issue | 4007-Report Spec 1=1 issue | 2012-03-08
| 3848 | Unit Name and Address missing from Subject and Victim Title Block of ROI and SCR | 3848-Unit Name and Address missing from Subject and Victim Title Block of ROI and SCR.sql | Skip -these are included in the CR3738 group below | Make sure we run 3738-Active and All Desktop FiltersActive and All Desktop Filters on the same day!!!!
| 3847 | ROI does not include AKA and NEE | 3847-ROI does not include AKA and NEE.SQL | Skip -these are included in the CR3738 group below
| 3923 | ROI Interview Title Block missing information | 3923-ROI Interview Title Block missing information.sql | 2012-03-14
| 3785 | Allow IG Role to view all cfunds in cfms | 3785-Allow IG Role to view all cfunds in cfms.sql | 2012-03-14
| 3949 | Allow Complete and Close all to work on 110's (Restricted Activities) | 3949-Allow Complete and Close all to work on 110's (Restricted Activities).sql | 2012-03-14
| 3589 | Need Privilege to Approve 106-A- Offenses | 3589-Need Privilege to Approve 106-A- Offenses.sql | 2012-03-14
| 3918 | Don't allow invalid DIBRS Offense Combinations | 3918-Don't allow invalid DIBRS Offense Combinations.sql | 2012-03-14
| 3271 | Classifications | 3271-Classifications.sql | 2012-03-14
| 3973 | Participant Name not displaying in ROI TOC for Search of Person | 3973-Participant Name not displaying in ROI TOC for Search of Person.sql | 2012-03-14
| 3789 | CFUNDS to EFUNDS, things missed the first time around | 3789-CFUNDS to EFUNDS, things missed the first time around.sql | 2012-03-14
| 3958 | Missing MAJCOM (Air Force Global Strike Command) | 3958-Missing MAJCOM (Air Force Global Strike Command).sql | 2012-03-14
| 3954 | Default other participant to Program for CSP files | 3954-Default other participant to Program for CSP files.sql | 2012-03-14
| 3952 | Change EFunds Paragraph A2.2.28 from USAFISIA Student Training to just Training | update.sql | 2012-03-14
| 3925 | DEERS Check fails if there are two Legal Names | OSI_DEERS-BODY_ONLY.sql | 2012-03-14
| 3977 3978 | Auto Print Tag Timing issue at Log In and Add it for Derivative Evidence | 3977, 3978-Auto Print Tag Timing issue at Log In and Add it for Derivative Evidence.sql | 2012-03-14
| 3985 | ROI TOC for Document Reviews not showing Subject of Activity | 3985-ROI TOC for Document Reviews not showing Subject of Activity\OSI_INVESTIGATION-BODY_ONLY | 2012-03-14
| 3771 3957 3974 | Number of Rows shown in Reports (ie Associations, Assignments) | 3974-Number of Rows shown in Reports (ie Associations, Assignments).sql | 2012-03-21
| 3655 | View Find Widget Button Alignments | 3655-View Find Widget Button Alignments\f100_page_30305.sql | 2012-03-21
|  | Opening objects from Links (ie, like from notifications) javascript error(s) | ####-Opening objects from Links (ie, like from notifications) javascript error(s)\f100_page_105.sql | 2012-03-08
| 3738 3964 3781 3742 3728 3727 3711 3646 3641 3639 3635 3623 3563 3497 3447 3446 | Active and All Desktop Filters | 3738-Active and All Desktop FiltersActive and All Desktop Filters | 2012-03-21 | See Implementation.doc***
| 3959 | Form 40 Report Fails when there is no lead agent | 3959-Form 40 Report Fails when there is no lead agent | 2012-03-21
| 3982 | checkcasesapproachingdaysopen still using code instead of sid | 3982-checkcasesapproachingdaysopen still using code instead of sid | 2012-03-21
| 3989 3990 3776 | AFOSI Applicant File Changes | 3989, 3990, 3776-AFOSI Applicant File Changes | 2012-03-21
| 3423 | Some CFunds Notifications go to the wrong unit | 3423-Some CFunds Notifications go to the wrong unit | 2012-03-21
|  | ####-T_DIBRS_REFERENCE Description Change | ####-T_DIBRS_REFERENCE Description Change | 2012-03-09
|  | ####-DSAIDS SAPRO Reference Data Load | ####-DSAIDS SAPRO Reference Data Load | 2012-03-14
|  | version_update | version_update.sql | 2012-03-21