## Sheet1
Test Results | CR# | Problem | Fixes Location | Applied in Production
Not Testable | 3893 | Participant Relationship Import from Legacy Issue | 3893-Participant Relationship Import from Legacy Issue\OSI_PARTICIPANT-BodyOnly.sql | 2011-06-20
Not Testable | 3894 | Buffer too small during Case File Pre-Closure Checklist | 3894-Buffer too small during Case File Pre-Closure Checklist\3894-Buffer too small during Case File Pre-Closure Checklist.sql | 2011-06-22
Passed | 3863 | Re-Opening a Case File takes it To Open instead of Investigatively Closed | 3863-Re-Opening a Case File takes it To Open instead of Investigatively Closed\OSI_STATUS_PROC.SQL | 2011-10-12
Passed | 3680 3868 3869 | SAPRO Incident and Subject Assigned Locations | 3680, 3868, and 3869-SAPRO Incident and Subject Assigned Locations | 2011-10-31 | See implementation.doc *** Also will need to load Military Installations, once SAPRO provides the list.
Passed | 3843 | Initial Notification Uses Subject instead of Notified in Narrative Generation | 3843-Initial Notification Uses Subject instead of Notified in Narrative Generation | 2011-10-12
Passed | 3566 | Allow Picking Subjects to Create Case from Info-Dev | 3566-Allow Picking Subjects to Create Case from Info-Dev | 2011-10-31
Passed | 3600 | Allow Creating DCII Indexing File from Dev-Info File | 3600-Allow Creating DCII Indexing File from Dev-Info File | 2011-10-31
Passed | 3571 | Add Offense to Initial Notification | 3571-Add Offense to Initial Notification | 2011-10-31
Passed | 3860 | Hide Fingerprint Screens Read-Only Message | 3860-Hide Fingerprint Screens Read-Only Message | 2011-10-31
Passed | 3895 | FD-249 screen showing too many dispositions | 3895-FD-249 screen showing too many dispositions | 2011-10-31
Passed | N/A | 092-A4 Offense needs property | 092-A4 Offense needs property | 2011-07-06
Passed | 3904 | Type Weapon Force Used using wrong DIBRS List | 3904-Type Weapon Force Used using wrong DIBRS List | 2011-07-12
Passed | 3857 3888 | Print Inventory before saving causes error and Complete Date Change Error | 3857, 3888-Print Inventory before saving causes error and Complete Date Change Error | 2011-10-31
Passed | 3874 | EMM Filter by File Save issue | 3874-EMM Filter by File Save issue | 2011-11-09 | Rolled Back, causing a Log Out Problem.
Passed | 3870 | Letter Of Notification Privacy Act Information | 3870-Letter Of Notification Privacy Act Information | 2011-11-09
Passed | 3859 | Participant Image now showing in Participant Details Report | 3859-Participant Image now showing in Participant Details Report | 2011-11-09
Not Testable | 3762 | Note Changes not being checked for Inactive Investigation notification | 3762-Note Changes not being checked for Inactive Investigation notification | 2011-11-09
Not Testable | 3706 | Notification for Investigatively Closed Activities | 3706-Notification for Investigatively Closed Activities | 2011-11-09
Passed | 3880 | ROI Narrative Sort Order issues | 3880-ROI Narrative Sort Order issues | 2011-11-09
Passed | 3881 | Add Amount Remaining to CFMS Screen | 3881-Add Amount Remaining to CFMS Screen | 2011-11-09
Passed | 3475 | Narrative Preview in Activities can cause Narrative Loss if not saved | 3475-Narrative Preview in Activities can cause Narrative Loss if not saved | 2011-11-09
Passed | 3871 | Rearrange ROI Narratives | 3871-Rearrange ROI Narratives | 2011-11-09
Passed | 3852 3853 3854 | IOC Roles Privs and New Consultation Types | 3852, 3853, and 3854 - IOC Roles Privs and New Consultation Types | 2011-11-09
Passed | 3789 | Change C-Funds to E-Funds | 3789-Change C-Funds to E-Funds | 2011-12-08
Passed | 3909 | EMM Rename the Split Tag to Derivative Evidence | 3909-EMM Rename the Split Tag to Derivative Evidence | 2011-12-08 | check logout problem from 3873
Passed | 3903 | Have Weapon Force Used points to the incorrect tab | 3903-Have Weapon Force Used points to the incorrect tab | 2011-12-08
Passed | 3855 3926 | Arrow through Notes and Narratives, Note Update and Add problem | 3855, 3926-Arrow through Notes and Narratives, Note Update and Add problem | 2011-12-08
Passed | 3902 | EFunds Paragraph and Receipts Changes | 3902-EFunds Paragraph and Receipts Changes | 2011-12-08
Passed | 3897 | New Major Command for Organizational Participant | 3897-New Major Command for Organizational Participant | 2011-10-12
Passed | 3884 | Pay Plan and Grade enable for Retirees and Memebers | 3884-Pay Plan and Grade enable for Retirees and Memebers | 2011-12-08
Passed | 3873 | Allow Sorting Attachments C20in the ROI Attachment Tab | 3873-Allow Sorting Attachments in the ROI Attachment Tab | 2011-12-08
Passed | 3928 | FD-249 Issues (Arrest Date, Agent Phone Number) | 3928-FD-249 Issues (Arrest Date, Agent Phone Number) | 2011-12-08
Passed | 3794 | AAPP Activity Restriction change from ASSIGN to UNIT | 3794-AAPP Activity Restriction change from ASSIGN to UNIT | 2011-12-08
Passed | 3866 | EMM Log In Evidence Changes | 3866-EMM Log In Evidence Changes | 2011-12-15 | check logout problem from 3873
Passed | 3610 | Confirm Logout, since logging out will log out all windows | 3610-Confirm Logout, since logging out will log out all windows | 2011-12-15 | See Implementation.doc***
Passed | 3935 | Reject should only Reject Submitted Evidence | 3935-Reject should only Reject Submitted Evidence | 2011-12-15 | check logout problem from 3873
Passed | 3934 | IG Roles and Privilege Changes | 3934-IG Roles and Privilege Changes | 2011-09-13
Not Testable | 3917 | Error in DEERS updates because of Multiple Relationships | 3917-Error in DEERS updates because of Multiple Relationships | 2011-12-15 | Needs Testing when DEERS connection is restored. ***********
Passed | 3916 | Inactive Paragraphs showing in CFMS | 3916-Inactive Paragraphs showing in CFMS | 2011-12-15
Passed | 3416 | Load Agents Assigned change to get associate file activities assignments | 3416-Load Agents Assigned change to get associate file activities assignments | 2011-12-15
Passed | 3905 | Activities Quick Note View in File Associations | 3905-Activities Quick Note View in File Associations | 2011-12-15 | See Implementation.doc***
Passed | 3940 | Another ROI Narrative Problem if larger that 32,000 characters | 3940-Another ROI Narrative Problem if larger that 32,000 characters | 2011-12-15
Passed | 3931 | ROI Date Format is incorrect | 3931-ROI Date Format is incorrect | 2011-12-15
Passed | 3929 | Letter Of Notification has incorrect Paragraph referenced | 3929-Letter Of Notification has incorrect Paragraph referenced | 2011-12-15
| 3927 | Form 2701 Checklist item for Witness and Victim Interviews | 3927-Form 2701 Checklist item for Witness and Victim Interviews | 2011-12-15
| 3944 | Add Fulltext Search Audit to T_OSI_AUDIT | 3944-Add Fulltext Search Audit to T_OSI_AUDIT | 2011-12-15
|  | CF_PROXY Command not given to any roles | ####-CF_PROXY Command not given to any roles.sql | 2011-10-19
|  | ####-Title 18 Offense Property Loss Mappings | ####-Title 18 Offense Property Loss Mappings | 2011-11-30
| 3967 | 3967-AAPP Permission changes | 3967-AAPP Permission changes\t_osi_auth_role_priv.sql | 2011-12-08
|  | version_update.sql | version_update.sql | 2011-12-15