## Sheet1
Scheduled Release Date | CR# | Problem | Fixes Location | Applied in Test System | Applied in Production | Special Instructions
22-Oct | 3474 4067 4085 | I2MS Local Mode Changes | 3474, 4067, 4085 - I2MS Local Mode Changes | 2012-10-12 | 2012-10-23
02-Nov | 4164 | Subject/Victim/Witness List Report has incorrect SSNs | 4164-Subject-Victim-Witness List Report has incorrect SSNs |  | 02-Nov
13-Nov | 4159 | Add Unit Personnel Records Group (UPRG) to Document Review Types | 4159-Add Unit Personnel Records Group (UPRG) to Document Review Types | 2012-11-20 | 26-Nov
13-Nov | #### | PHP Installation | ####-PHP Installation | 2012-10-26 | 23-Nov | *** SEE IMPLENTATION NOTE.DOC ***
13-Nov | 4026 | Add Document Review Type - Surveillance Activity Data Review | 4026-Add Document Review Type - Surveillance Activity Data Review | 2012-11-20 | 2012-11-26
13-Nov | #### | More P0_OBJ page Branching things (ACTIVITIES) | ####-More P0_OBJ page Branching things (ACTIVITIES) | 2012-11-20 | 2012-11-26 | 36 Pages
13-Nov | #### | More P0_OBJ page Branching things (FILES,PARTS) | ####-More P0_OBJ page Branching things (FILES,PARTS) | 2012-11-20 | 2012-11-26 | 58 Pages
13-Nov | !!!!!! | Page 0 P0_TABS issues when reloading | !!!!!!####-Page 0 P0_TABS issues when reloading | 2012-11-20 | 2012-12-10
13-Nov | 4104 | &, ~, and others character problems in Address Widget | 4104-&, ~, and others character problems in Address Widget | 2012-11-20 | 2012-12-10 | Moved Below 4104 because of 22610 and 11505
13-Nov | #### | JavaScript Cleanup - get rid of JS_POPUP_OBJ_DATA | ####-JavaScript Cleanup - get rid of JS_POPUP_OBJ_DATA | 2012-11-20 | 2012-12-10 | *** SEE IMPLENTATION NOTE.DOC *** | *** Shared components not removed (see instructons)
13-Nov | 4083 | Allow Multiple Work Hour Entries at once | 4083-Allow Multiple Work Hour Entries at once | 2012-11-20 | 2012-12-10 | *** SEE IMPLENTATION NOTE.DOC ***
13-Nov | #### | Changed IAFIS screen to jQuery Dialog | ####-Changed IAFIS screen to jQuery Dialog | 2012-11-20 | 2012-12-10
13-Nov | 4106 | Double Clicking Save during Object Creation can cause it to create multiples | 4106-Double Clicking Save during Object Creation can cause it to create multiples | 2012-11-20 | 2012-12-11 | Run on the Same Day Please!!!! *** SEE IMPLENTATION NOTE.DOC ***
13-Nov | 4104 | &, ~, and others character problems in Address Widget | 4104-&, ~, and others character problems in Address Widget | 2012-11-20 | 2012-12-10 |  | REAPPLIED 22610 and 11505 14-Dec-2012 in Production.
13-Nov | #### | Changing other popups to jQuery Dialog Window | ####-Changing other popups to jQuery Dialog Window | 2012-11-20 | 2012-12-11 |  | *** Shared components not removed (see instructons)
13-Nov | 4116 | Received and Seized from Participant in Evidence Tags | 4116-Received and Seized from Participant in Evidence Tags | 2012-11-20 | 2012-12-11 | Run Together!!!! Run same day as ####-More P0_OBJ page Branching things (FILES,PARTS) and ####-Changing other popups to jQuery Dialog Window (Patches all include Pages 30700 and 30710)
13-Nov | 3999 4034 | FIX to Multiple Login Problems and Reject Evidence Error | 4034-FIX to Multiple Login Problems and 3999-Reject Evidence Error | 2012-11-20 | 2012-12-11
13-Nov | 4147 | Narrative on the Activity Associations Screen | 4147-Narrative on the Activity Associations Screen | 2012-11-20 | 2012-12-11
13-Nov | 4111 | Rows resets after sorting columns | 4111-Rows resets after sorting columns | 2012-11-20 | 2012-12-11
13-Nov | 4108 | New DIBRS Race Codes | 4108-New DIBRS Race Codes | 2012-11-20 | 2012-12-11
| 4224 | Add Participant Version is Broken | 4224-Add Participant Version is Broken | 2013-01-09 | 2013-01-09 | MUST BE RUN AFTER --####-Changing other popups to jQuery Dialog Window
| 4233 | RTF Characters in Narrative of Form 40s and ROIs | 4233-RTF Characters in Narrative of Form 40s and ROIs | 2013-01-17 | 2013-01-17 | This also implements 3806, 4160, 4162, 4163, 3911, 3943, and 3981
| 3806 4160 | Allow Agents to delete their own activities as long as it passes the other checks | 3806, 4160-Allow Agents to delete their own activities as long as it passes the other checks | 2013-01-17 | 2013-01-17 | ***** SEE 4233 *****
| 4162 4163 | Get rid of (SUBJECT) in the Form 40 remarks, Attachment Listing | 4162, 4163-Get rid of (SUBJECT) in the Form 40 remarks, Attachment Listing | 2013-01-17 | 2013-01-17 | ***** SEE 4233 *****
| 4129 | Units without parents not showing in Desktop or Locators | 4129-Units without parents not showing in Desktop or Locators | 2013-01-22 | 2013-02-11
| 4112 | Type of Criminal Activity shows incorrect values | 4112-Type of Criminal Activity shows incorrect values | 2013-01-22 | 2013-02-11
| 4088 | New Offense Code Title 18 207 | 4088-New Offense Code Title 18 207 | 2013-01-22 | 2013-02-11
| 3911 3943 3981 | Letter of Notification Paragraph missing | 3911, 3943, 3981-Letter of Notification Paragraph missing | 2013-01-17 | 2013-01-17 | ***** SEE 4233 *****
| 4255 | NIBRS OFFENSES 210 require Weapon and Injury | 4255-NIBRS OFFENSES 210 require Weapon and Injury |  | 2013-02-15 | REQUIRED FOR USER TO GET THROUGH CLOSURE CHECKLISTS
| #### | jQuery Upgrade to 1.8.3 and jQuery UI to 1.9.1 | ####-jQuery1.8.3UI1.9.1 | 2013-01-23 | 2013-02-20 | *** SEE IMPLENTATION NOTE.DOC ***
| 3671 | Age Validation issues | 3671-Age Validation issues | 2013-01-23 | 2013-02-20 | ****** MUST BE RUN AFTER Jquery Upgrade NOT BEFORE ******
| 3970 4122 | New Offense Codes | 3970 and 4122-New Offense Codes | 2013-01-23 | 2013-02-20
| 4141 | Consultation and Coordination Create Privilege | 4141-Consultation and Coordination Create Privilege |  | 2012-12-18
| 4118 | EMM Desktop Right Click issues | 4118-EMM Desktop Right Click issues | 2013-01-23 | 2013-02-20
| 4098 4114 4117 4127 | Surveillance Changes and Create Activity Screen (21001) combo box and arrow keys | 4098, 4114, 4117, 4127-Surveillance Changes and Create Activity Screen (21001) combo box and arrow keys | 2013-01-23 | 2013-02-20
| 4105 | Reviewer Note Tab in the PMM | 4105-Reviewer Note Tab in the PMM | 2013-01-23 | 2013-02-20
| 3426 | Shouldn't have to check Reserve Affiliation for UKNOWN participants | 3426-Shouldn't have to check Reserve Affiliation for UKNOWN participants | 2013-01-23 | 2013-02-20
| 3633 | Gray out Reserve stuff if Regular is picked as the US Service Affiliation Component | 3633-Gray out Reserve stuff if Regular is picked as the US Service Affiliation Component | 2013-01-23 | 2013-02-20
| 3950 | PMM Role given to All OSI is not allowing correctly | 3950-PMM Role given to All OSI is not allowing correctly | 2013-01-23 | 2013-02-21
| 4132 | Remove Coordination, Forensics (non-computer) from I2MS | 4132-Remove Coordination, Forensics (non-computer) from I2MS | 2013-01-23 | 2013-02-21
| 4134 | Allow Ending Assignments without having to load each assignment record | 4134-Allow Ending Assignments without having to load each assignment record | 2013-01-23 | 2013-02-21
| 4135 | Add 2701 to the Create Activity Screen for Interview | 4135-Add 2701 to the Create Activity Screen for Interview | 2013-01-23 | 2013-02-21
| 4187 | Time not saving for Coordination and Consultation Activities | 4187-Time not saving for Coordination and Consultation Activities | 2013-01-23 | 2013-02-21
| 3588 | Squadron Analyst Role | 3588-Squadron Analyst Role | 2013-01-23 | 2013-02-21
| 4057 | Allow Region Vice Commander to grant the Region IMA Commander Role | 4057-Allow Region Vice Commander to grant the Region IMA Commander Role | 2013-01-23 | 2013-02-21
| 3327 | Only HQ can approve 106 and 106a offenses | 3327-Only HQ can approve 106 and 106a offenses | 2013-01-24 | 2013-02-21
| 3710 3861 | JQuery Multiple File Uploading | 3710, 3861-JQuery Multiple File Uploading | 2013-02-22 | 2013-02-27 | *** SEE IMPLENTATION NOTE.DOC ***
| 4133 | Add Search of Cyber Device to Search Activity | 4133-Add Search of Cyber Device to Search Activity | 2013-02-22 | 2013-02-27
| #### | jQuery Resizable Panels, Slow down the Menus | ####-jQuery Resizable Panels, Slow down the Menus | 2013-02-22 | 2013-02-27 | *** SEE IMPLENTATION NOTE.DOC ***
| 3988 | Notification - Investigative Plan not attached in 5 days of case approval | 3988-Notification - Investigative Plan not attached in 5 days of case approval | 2013-02-22 | 2013-02-27
| 4173 | Case Status Report IDP Page Removal | 4173-Case Status Report IDP Page Removal | 2013-02-22 | 2013-02-27 | *** SEE IMPLENTATION NOTE.DOC ***
| 4149 | EMM incorrectly displays evidence that was received from a participant | 4149-EMM incorrectly displays evidence that was received from a participant | 2013-02-22 | 2013-02-27
| 4145 | Allow user to Lock and Unlock their own Notes | 4145-Allow user to Lock and Unlock their own Notes | 2013-02-22 | 2013-02-27
| 4186 | SCR Can be deleted | 4186-SCR Can be deleted | 2013-02-22 | 2013-02-27
| 4171 | Add DoD ID Number for Creating Participants from DEERS | 4171-Add DoD ID Number for Creating Participants from DEERS | 2013-02-22 | 2013-02-27
| 3991 | ORI, Address, POB State and Country wrong on printed FD-249 | 3991-ORI, Address, POB State and Country wrong on printed FD-249 | 2013-02-22 | 2013-02-27
| 4248 | Form2 Location is incorrect | 4248-Form2 Location is incorrect | 2013-02-22 | 2013-02-27 | ….CAN BE RUN ANYWHERE HERE….
| 4165 4185 4205 | Ready for Review and Form 40 Signed Attached | 4165, 4185, 4205-Ready for Review and Form 40 Signed Attached | 2013-02-22 | 2013-02-27 | *** SEE IMPLENTATION NOTE.DOC ***
| 4197 | Showing Full-ID on Desktop View and in Files when possible | 4197-Showing Full-ID on Desktop View and in Files when possible | 2013-02-22 | 2013-02-27 | Was moved from above 4165,4185,2305 because it overwrote that change in OSI_DESKTOP (found in testing).
| #### | Set max attachment limit | ####-Set max attachment limit | 2013-02-22 | 2013-02-27
| 4247 | Give Tech Agents and Managers privilege to create technical consultations | 4247-Give Tech Agents and Managers privilege to create technical consultations | 2013-01-30 | 2013-01-30
|  | version_update | version_update.sql | 2013-02-22 | 2013-02-27