## Sheet1
Estimated Size | CR# | Problem | Fixes Location | Applied in Test System | Applied in Production | Special Instructions
Small | 4200 | Badge Number Check needs to be less than or equal to 2800 | 4200-Badge Number Check needs to be less than or equal to 2800 |  | 05-Dec-12
Small | 4288 | Part I, change Coordination Create Menu to .ACQUISITION | 4288-Part I |  | 19-Mar-13
Small | 4298 | Document Review and LERC Clone broken | 4298-Document Review and LERC Clone broken\Fix directly for Production |  | 26-Mar-13 | Fix in 4231, Fix+comment in 4262.
Small | 4304 | Unlock ROI Draft Template | 4304-Unlock ROI Draft Template |  | 04-Apr-13
Small | #### | Turn Pipes off | ####-Turn Pipes off | 2013-04-23 | 30-Apr-13
Small | 4293 | New WebLinks Menu | 4293-New WebLinks Menu | 2013-04-10 | 30-Apr-13 | *** SEE IMPLENTATION NOTE.DOC ***
Small | 4302 | Case Report Types re-arrange and re-name | 4302-Case Report Types re-arrange and re-name | 2013-04-10 | 30-Apr-13
Small | 4253 | On Notification of Opened Case, distiguish between Open or ReOpen | 4253-On Notification of Opened Case, distiguish between Open or ReOpen | 2013-04-10 | 30-Apr-13
Small | 4254 | Add Tech Advice note to Consultation activities | 4254-Add Tech Advice note to Consultation activities | 2013-04-23 | 30-Apr-13
Small | 4260 | Subject not carried over during Initial Notification Case Creation | 4260-Subject not carried over during Initial Notification Case Creation | 2013-04-23 | 30-Apr-13
Small | #### | JQuery Dialog Box Min and Max Buttons | ####-JQuery Dialog Box Min and Max Buttons | 2013-04-23 | 30-Apr-13 | *** SEE IMPLENTATION NOTE.DOC ***
Small | 4174 | Activity Create Work Hours Duty Category is being left blank, causes error | 4174-Activity Create Work Hours Duty Category is being left blank, causes error | 2013-04-23 | 30-Apr-13
Small | 4193 | LERC and DOC Review Details Narrative Box Size and Report Column Size | 4193-LERC and DOC Review Details Narrative Box Size and Report Column Size | 2013-04-23 | 30-Apr-13
Small | 3432 | 120A--Should be Sex and General Crimes | 3432-120A--Should be Sex and General Crimes | 2013-04-23 | 30-Apr-13
Small | 4206 | Title clears on File Association in Activity Creation | 4206-Title clears on File Association in Activity Creation | 2013-04-23 | 30-Apr-13
Small | #### | Dialog Cancel multiple times | ####-Dialog Cancel multiple times | 2013-04-23 | 01-May-13
Small | 4100 | Problem with Export doing f as the filename | 4100-Problem with Export doing f as the filename | 2013-04-23 | 01-May-13
Small | 3456 | Change EMM Print Manual Tag Button | 3456-Change EMM Print Manual Tag Button | 2013-04-23 | 01-May-13
Small | 4190 | Property Tab Issues | 4190-Property Tab Issues | 2013-04-23 | 01-May-13
Small | #### | Get rid of blank white box on associations screen | ####-Get rid of blank white box on associations screen | 2013-04-23 | 01-May-13
Medium | 4236 | DocRev and LERC showing in Activity Association Screen | 4236-DocRev and LERC showing in Activity Association Screen | 2013-04-23 | 01-May-13
Medium | 4241 | New CAT and NNRIA Checklist Activities | 4241-New CAT and NNRIA Checklist Activities | 2013-04-24 | 01-May-13
Small | #### | Index Fixes for Reporting | ####-Index Fixes for Reporting | 2013-04-24 | 02-May-13
Large | 3968 4234 4280 | Submit to USACIL button, allow clone to clone attachments | 3968, 4234, 4280-Submit to USACIL button, allow clone to clone attachments | 2013-05-07 | 14-May-13 | ***************************************** REQUIRES A RELEASE OF SENDREQUEST.EXE ***************************************** | Sets MAX # Files uploaded to 10.
Small | 4246 | Add D-DEx to Law Enforcement Records Checks | 4246-Add D-DEx to Law Enforcement Records Checks | 2013-05-07 | 14-May-13
LARGE | #### | Upgrade jQuery 1.9.1, UI 1.10.2 | ####-jQuery1.9.1&UI 1.10.2 | 2013-05-07 | 14-May-13 | *** SEE IMPLENTATION NOTE.DOC ***
Small | 4219 4244 | EFunds Expense Issues | 4219, 4244-EFunds Expense Issues | 2013-05-07 | 14-May-13
Small | 4231 | First Character of Narrative lower case for DOCREV and LERC | 4231-First Character of Narrative lower case for DOCREV and LERC | 2013-05-07 | 14-May-13
Small | 4230 | Show first 50 characters of Notes | 4230-Show first 50 characters of Notes | 2013-05-07 | 14-May-13
Small | 4223 | Two Mailing Addresses breaks DEERS Compare | 4223-Two Mailing Addresses breaks DEERS Compare | 2013-05-07 | 14-May-13
Small | 4220 | Have Specification Jurisdictions goes to the wrong tab | 4220-Have Specification Jurisdictions goes to the wrong tab | 2013-05-09 | 14-May-13
Small | 4245 | New Field on Consultation, Technical Services | 4245-New Field on Consultation, Technical Services | 2013-05-09 | 14-May-13
Small | 4225 | LERC and DOC Review Narrative and Title resetting during create | 4225-LERC and DOC Review Narrative and Title resetting during create | 2013-05-09 | 14-May-13
Small | 4243 | Info and Dev Dispo and Spec checklist items | 4243-Info and Dev Dispo and Spec checklist items | 2013-05-09 | 14-May-13
Small | 4227 | EMM Appellate and Congress Review | 4227-EMM Appellate and Congress Review | 2013-05-09 | 14-May-13
Small | 4256 | Fix Datepicker on IR Filters | 4256-Fix Datepicker on IR Filters | 2013-05-09 | 14-May-13 | ** ONLY CHANGED jquery-datetimepicker.js ** | Stop Here **
Medium | 4261 4305 | Release Notes Link on Desktop Page and UCO Interest Prompt | 4261,4305-Release Notes Link on Desktop Page and UCO Interest Prompt | 2013-05-16 | 21-May-13 | *** SEE IMPLENTATION NOTE.DOC ***
Small | 4263 | Age displaying incorrectly | 4263-Age displaying incorrectly | 2013-05-16 | 21-May-13
Medium | #### | Make any center pages open page 1000 | ####-Make any center pages open page 1000 | 2013-05-16 | 21-May-13 | *** SEE IMPLENTATION NOTE.DOC *** | CAN'T BE RUN BEFORE jQuery Upgrade
Small | ####- | Minor issues with OSI_DESKTOP participant and Files Views | ####-Minor issues with OSI_DESKTOP participant and Files Views | 2013-05-16 | 21-May-13
Small | 4262 | Activity Date on Summary tab of DocRev and LERC Activities | 4262-Activity Date on Summary tab of DocRev and LERC Activities | 2013-05-16 | 21-May-13
Small | 4269 | End Assignments on Files when Closed | 4269-End Assignments on Files when Closed | 2013-05-16 | 21-May-13
Small | 4283 | Ending Role in PMM gives an error | 4283-Ending Role in PMM gives an error | 2013-05-16 | 21-May-13
Small | 4250 4267 4268 | Form 40 ROI Changes | 4250, 4267, 4268-Form 40 ROI Changes | 2013-05-16 | 21-May-13
Small | 4196 | EMM Minimum Effective Date on Transactions | 4196-EMM Minimum Effective Date on Transactions | 2013-05-16 | 21-May-13
Medium | 3951 | Evidence Custody Change Action | 3951-Evidence Custody Change Action | 2013-05-16 | 21-May-13
Small | !!!!!!! | Report Header in IE would scroll up in 10150 when the "View/Edit" icon was clicked | !!!POST RELEASE FIXES |  | 21-May-13 | OSI.CSS change only
Small | #### | Release notes Link gives Security Warning | !!!POST RELEASE FIXES\####-Release notes Link gives Security Warning |  | 23-May-13 | 1006 Page Change - Link now points to downloading the release notes from OSILink. | ALSO CHANGED MIME.TYPES and put it there but it will not fix DOCX and XLSX downloads unit the web service is restarted!
Small | #### | ####-Timestamp on Coordination Activities disappearing | !!!POST RELEASE FIXES\####-Timestamp on Coordination Activities disappearing |  | 28-May-13 | Applied trigger change only
Small |  | version_update | version_update.sql | 2013-05-16 | 21-May-13